## Test summary report
Tester | Team 104
Date | 2023-08-29
ID | Feature Name | Total number of test cases | Number of passed test cases | Number of failed test cases
UC01 | Edit profile | 4 | 3 | 1
UC02 | View profile | 2 | 1 | 1
UC03 | View Health Records | 3 | 2 | 1
UC04 | Modify Health Records | 11 | 11 | 0
UC05 | Health Monitoring | 3 | 2 | 1
UC06 | Food portion | 4 | 3 | 1
UC07 | View BMI value | 3 | 3 | 0
UC08 | Login account | 8 | 8 | 0
UC09 | Register account | 4 | 4 | 0
| Number of functions tested | 9 | Number of defects found | 30
| Total number of test cases | 42 | Number of closed bug reports | 29
| Total number of passed test cases | 37
| Total number of failed test cases | 5

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | The system accepts inappropriate fullname | The user put inappropriate fullname in the form on the edit profile page. The field "Fullname" still accepts the value (For example: typing "123" in the Fullname field is still valid) | UC01 | Low | Ngo Pham Huy Hoang | 2023-09-01 | Closed | Solution: Validating the data input for fullname field carefully (checking special symbols, length, .etc)
B002 | The system accepts invalid data while user editting their profile | The user edits their profile in the form on the edit profile page, it still confirms successfully even when the data is invalid (Examples: Year of birth is higher than current year) | UC01 | Medium | Le Xuan Dat | 2023-09-01 | Closed | Solution: Validating the data in the form before submitting, until then the submit button will be disabled
B003 | The system accepts non-existent country name | The country input field in the update form is a text input, which will accept every text, including inappropriate or non-existent country name. Worth noticing that the system still accepts that input | UC01 | Low | Le Xuan Dat | 2023-09-01 | Closed | Solution: change the text input into the selection input, limit user's choices to just the available country names
B004 | Error in displaying data | The user access to the profile page and the data profile that get from the server is not wrap a new line when the length of data is big. (Examples: The data is address or email, which has high length of it.) | UC02 | Low | Le Xuan Dat | 2023-09-01 | Closed | Note: add a CSS style 'wrap-text' to the container
B005 | Missing responsive behaviours for the UI | The responsive behaviours for the page haven't been implemented, thus making the web page weird when chaging size | UC02, UC03, UC05, UC06 | Medium | Tran Hoang Lam | 2023-08-29 | Open | Note: The same defects are found in some test cases, instead of stating out all of them, we stated it as a single defect Front End team is new to web-coding language, they can't fix this defect
B006 | Filter button doesn't filter correctly | Data got deleted after filtering, making the next filter bugged (show nothing) | UC03 | High | Tran Hoang Lam | 2023-08-29 | Closed | Cause: didn't use a temp variable to store the filtered data but instead assign it to the variable storing the data fetched from BE
B007 | Sort option isn't applied after filtering | On the next filtering, the previous option for sorting health records (latest/oldest) isn't applied | UC03 | Medium | Tran Hoang Lam | 2023-08-29 | Closed | Cause: didn't use sort function again after filltering box's option got changed
B008 | Simutaneously open every record's detailed information | Clicking on a record for detailed information triggers other records' accordions as well | UC03 | Medium | Tran Hoang Lam | 2023-08-29 | Closed | Cause: each record has an ID, but it wasn't properly used to distinguish between accordion objects
B009 | Null information fields in the health record view. | When the view health record has some information fields showing null | UC03 | Medium | Pham Uyen Nhi | 2023-08-31 | Closed | The json controller file sent to the view has fields that do not match the front end, so the solution is to rename the columns when querying the database in the getUserHealthRecord function
B010 | Update form's input fields aren't reset after switching to another record | The update form is shared between health records, so when users update a record and switch to another one, the old input data from the former update is still there | UC04 | Medium | Tran Hoang Lam | 2023-08-29 | Closed | Solution: reset the fields each time an update button is clicked
B011 | Typos in add/update form | The measurement for blood sugar is "mg/dL", not "mg/Dl" | UC04 | Low | Tran Hoang Lam | 2023-08-29 | Closed
B012 | Intentional alterations affect the accuracy of health record submission dates. | The submission date of health records becomes inaccurate due to intentional alterations made before submission. | UC04 | Medium | Pham Uyen Nhi | 2023-08-31 | Closed | The solution is not to receive submit_date from the frontend, we will use the Date() function on backend to get the current date
B013 | Duplicate records overload the health monitor chart, obscuring data. | When user add too many duplicate records at the same time, the chart on the health monitor will overlap (can't show the variation of health indicators) | UC04 | Medium | Pham Uyen Nhi | 2023-08-31 | Closed | The solution is to only allow a user to add only 1 health record for a day, when the user submits a health record, it will check in the database to see if that date has been added or not, if so, it will not accept that new record.
B014 | Delete all records instead of only one | When click "delete record" icon, instead of deleting only this record of user, the website deletes all records | UC04 | High | Pham Uyen Nhi | 2023-08-31 | Closed | The reason is because the query is wrong, the solution is to compare both record ID and user ID
B015 | The user fills all fields correctly, but still receives an unsuccessful submission message. | The user has filled in all the information fields, the form has been checked and found that the information fields are valid, but after submitting it still returned an unsuccessful message | UC04 | Medium | Pham Uyen Nhi | 2023-08-31 | Closed | Frontend sends the packet only in string data type, not matching database and some other processing functions (last submit date comparison). Solution is the Backend to parse the data type corresponding to the definition in the database before processing
B016 | Charts' color is too colorful | The colors used for making charts are too bright, also they are non-gradient, which makes a big bright block of color in the UI | UC05 | Low | Tran Hoang Lam | 2023-08-29 | Closed
B017 | Charts are too pointy | The lines in the charts need to be curvy, not just straight lines | UC05 | Low | Tran Hoang Lam | 2023-08-29 | Closed | Solution: add an attribute "tension" inside the option of the Charts
B018 | Drag event triggers click event | Dragging the overflown container triggers the button inside that container which the mouse is pointed to | UC05 | Medium | Tran Hoang Lam | 2023-08-29 | Closed | Solution: remove this drag event, use scroll bar instead
B019 | Unable to get resource files from /publics | Some pages are rendered (recipe, 404), but some files included by them (css, pictures, scripts) cannot be accessed. | UC06 | High | Tran Hoang Lam | 2023-08-29 | Closed | Cause: using relative path in href instead of absolute path
B020 | The contents inside the buttons are overflown | The category names are so long that they make the button stretched out from pill button to rounded border button | UC06 | Low | Tran Hoang Lam | 2023-08-29 | Closed | Solution: 1. Increase the fixed width of the button, 2. Shorten the category names
B021 | The button's background color doesn't change after choosing another button | When choosing another category by clicking a button, the previously chosen button's background color isn't changed back to the unselected theme color | UC06 | Medium | Tran Hoang Lam | 2023-08-29 | Closed
B022 | The BMI bar indicator doesn't work properly | The bar indicating the users' BMI level isn't working, it should change the size of the selected level based on BMI value | UC07 | Medium | Tran Hoang Lam | 2023-08-29 | Closed
B023 | Typos in page's content | There are some typos in the BMI page, especially inside the info content box | UC07 | Low | Tran Hoang Lam | 2023-08-29 | Closed
B024 | Send OTP in unregister email | Unregistered email still confirm successfully when require sending otp | UC08 | Medium | Pham Uyen Nhi | 2023-08-31 | Closed | The reason is the email has not been checked (is it in the database yet?), solution: check email before send otp
B025 | Can not access with correct password | Enter the correct password but login failed message | UC08 | Medium | Pham Uyen Nhi | 2023-08-31 | Closed | Hashed password can't be matched again, the reason is because each time the support function will hash a password, it can't be compared == like a normal string, it needs a compare function supported from the library
B026 | "Wrong OTP allows access to password reset page." | Even if the user enters the wrong OTP, it still confirms successfully and moves to the password reset page | UC08 | Medium | Pham Uyen Nhi | 2023-08-31 | Closed | Because the keyword setup in the airtable api link is wrong, instead of "filterByFormula" it's just a "filter". Solution is fix that keyword
B027 | Unregistered email access website | An unregistered account can login successfully to website | UC08 | High | Le Xuan Dat | 2003-09-01 | Closed
B028 | Unregistered email input in forget password page | The user input a unregister email in forget password page and the website continue to access to a OTP page | UC08 | Medium | Le Xuan Dat | 2003-09-01 | Closed
B029 | The system accepts invalid new password | The user reset password in account with password contain invalid data (Example: password is 1, which is invalid because the protection is rarely high), but the system still accepts the input | UC08 | High | Le Xuan Dat | 2003-09-01 | Closed | Solution: Validating data before submit, the user can not submit if the data is still invalid
B030 | The system accepts invalid password for login | The user register an account with password containing invalid data (Example: password is 1, which is invalid because the protection is rarely high), but the system still accept the input | UC09 | High | Le Xuan Dat | 2003-09-01 | Closed | Solution: Validating data before submit, the user can not submit if the data is still invalid